## ToDo
Sno | Description | Tag(Dev,Unit test, Integration test, End-End test) | ToDo(priority)
1 | Create landing page | Dev | Low
2 | Fetching the AI output data to the wallet | Dev | High
3 | Updating output values - The value field needs to be changed with a rating scale of 1-5 along with the current output | Dev | High
4
5
6
7
8
9
10
11

## Inprogress
Sno | Description | Tag(Dev,Unit test, Integration test, End-End test) | Priority
1 | Product name from the customer to database | Dev | High
2 | Fetching product name to the front end page | Dev | High
3
4
5
6
7
8
9
10
11
12
13
14

## Completed
Sno | Description | Tag(Dev,Unit test, Integration test, End-End test) | Priority
1 | Initial python code which is shared has to be modified interms of enviornment(Google colab to Vs studio) ,input data to make the code functional. | Dev | Med
2 | There was excess lines of code and hardoded values in the code which has been removed especially the input image format, the hardoded names of the image filenames(code dynamically takes the data from the target folder). | Dev | Pyhton code fixes for reusability (High)
3 | New python code has been developed to accommodate the use of fast api which serves as the backend api server. Degraded python version to 3.11x to accommodate pytorch library because few errors was popping up during the AI model functionality test. | Dev | New Python code for Fast API integration(High)
4 | We were able to successfully bring the information in the fastapi server with respect to the damaged shoe images that we are uploading. | Unit test | Testing the API response of the ML model on Fast API server(High)
5 | Ngork was introduced to expose the the fastapi backend to the internet and making it acessible to bubble.io and any other external services(Bubble.io is a cloud based platform and it cannot directly access the localhost ) | Dev | Introduced Ngrok to publically access the ML model(High)
6 | Ngork account was created which helps in creating autherisation token and generated public URL using command prompt. This URL is used as the POST method URL(ex - https://06eb-159-2-59-236.ngrok-free.app/process-image/). We are using the unpaid version of ngork and the limitation is that whenever we close and reopen the tunnel the URL will get changed and the same needs to be replaced in the bubble.io API connector configuration as well. | Dev | Enviornment set up for the Ngrok autherisation(High)
7 | The API connector needs to be created and configured accordingly with the relevant settings(For more details on the setting login to bubble app and check the api connector with name FastAPI Image Processing and the API call name Upload Image for all the config details). Once configured we have re-initialized the call to get the details. We can also attach the file in the configuration setting to test it internally. We faced issue in parsing information which resulted in changing the JSON response structure and making it more easier to parse. Also we have manually entered the API response structure so the app can easliy fetch each of the individual details like Name of product, Era, value etc... | Dev | Creating and Enabling API connector in Bubble.io(High)
8 | Testing done to make sure the Ngrok has communication between Fast Api server. | Unit test | Testing the Ngrok response
9 | Integration test has been performed where we have uplaoded the image in the gluu repair website and when clicked on the submit the website was effectively able to communicate with AI Model returning a '200 OK' response in the command prompt | Integration test | Integration test(Ngork,fast api and AI model functionality)
10 | Creating text fields in Bubble.io and inserting dynamic data from AI model output - The generated response now needed to be shown in the front-end fields against each of name of product , material etc(Parse JSON response and allocate to each of the respective fields). Text field has been created against each of the fields and dynamic data has been inserted by variables which we have created for API calls. Even though we were able to pull the information the data was not aligned to the corresponding fields. | Dev | Creating text fields in Bubble.io and inserting dynamic data from AI model output
11 | While doing the integration test, the bubble.io was throwing error on the limitation of the application saying that it has reached to limit of data that can be entered. We troubleshoot and finally able to move the process to a separate copy of the gluu.repair website(Initially we were working on the backup version and now we have moved and started to work on the Gluu.repair version ). Once we we started to use the Gluu.repair we were able to figure out many data which was unnecessary stored in the backend database tables, which were deleted and proceeded with the integration testing. The integration testing was success. | Integration test | Integration test(Bubble.io,Ngork,fast api and AI model functionality)
12 | The alignment of the values which we brought to the front end was not satisfactory and moreover it was misplaced, so we have figure out the term of 'grouping each element' and also to group them in a 'row container' . Later spacing and width is adjusted to provide proper alignment for the output. | Dev | Fixing alignment issue in the front end of website
13 | Integration test has been performed after making this changes and showed the demo of the so far progress of the project to the product owner. | Integration test | Integration test(Bubble.io,Ngork,fast api and AI model functionality)
14 | Add trigger to insert values to the database | Dev | High
14 | Unit Test - Add trigger to insert values to the database | Unit test | High